***To Whom It May Concern,***

*Fortnightly Newsletter* No. 2.

The *Contractor’s* [*Circet Networks (Ireland)*] *Web Page* may be viewed

[Duke St, Anne St South Public Realm Project](https://eur03.safelinks.protection.outlook.com/?url=https%3A%2F%2Fscanner.topsec.com%2F%3Fd%3D3276%26r%3Dauto%26u%3Dhttps%253A%252F%252Fwww.worksupdates.com%252Fdcc%252F%26t%3D4d7cd844bf1e1f0b24163bed67dbb2e26ac756e6&data=05%7C02%7Cturlough.nolan%40circet.ie%7C6cb1adc457de4bbb82d108ddf775ed44%7Cbdb24001a6cd45029ba50ae01a69955b%7C1%7C0%7C638938808079447118%7CUnknown%7CTWFpbGZsb3d8eyJFbXB0eU1hcGkiOnRydWUsIlYiOiIwLjAuMDAwMCIsIlAiOiJXaW4zMiIsIkFOIjoiTWFpbCIsIldUIjoyfQ%3D%3D%7C0%7C%7C%7C&sdata=IeCmqP6BuAf4OgHmsldFj3w%2B0epGy%2FlW83iAVHuvDEw%3D&reserved=0)

The *Employer’s* [DCC’s] *Web Page* may be viewed

[Duke St, Anne St South Public Realm Project | Dublin City Council](https://eur03.safelinks.protection.outlook.com/?url=https%3A%2F%2Fscanner.topsec.com%2F%3Fd%3D3276%26r%3Dauto%26u%3Dhttps%253A%252F%252Fwww.dublincity.ie%252Froad-maintenance%252Four-road-improvement-plans%252Fduke-st-anne-st-south-public-realm-project%26t%3Da5e242d13f713f77a7895a8e31a7d6a5679365a9&data=05%7C02%7Cturlough.nolan%40circet.ie%7C80d09e81c52942e9356c08ddefb136cd%7Cbdb24001a6cd45029ba50ae01a69955b%7C1%7C0%7C638930266610109847%7CUnknown%7CTWFpbGZsb3d8eyJFbXB0eU1hcGkiOnRydWUsIlYiOiIwLjAuMDAwMCIsIlAiOiJXaW4zMiIsIkFOIjoiTWFpbCIsIldUIjoyfQ%3D%3D%7C0%7C%7C%7C&sdata=Wp3q2rfWCsf1KdbgPcwu1p7SPOmZA7zD3RI%2FDQR6rxQ%3D&reserved=0)

*Roadworks’ Contractor, Circet Networks (Ireland)* is happy to share with you, and one and all, today’s *Fortnightly Newsletter* (2).

**1.            Last Two Weeks – History**

* Respectfully maintained Stakeholder Comms in all Works’ Matters.
* South Anne St – Northern footpath complete between Grafton St and Duke Lane Upper.
* Duke St – 15m of paving installed on southern footpath from the Grafton St end.

2.            **Next Two Weeks – Plan**

* Respectfully maintain Stakeholder Comms in all Works’ Matter.
* South Anne St – Commence excavation and paving between Grafton Street and Anne’s Lane along carriageway starting at Grafton St side.
* Duke St – Continue excavating and paving between Grafton Street and Duke Lane Upper southern footpath starting at Grafton St side.

Meanwhile, and of course, deliveries (on South Anne St) will be accommodated to local premises via the eastern end of South Anne St and Grafton St. If you have any need(s), please let the *Contractor* know.

3.            **Temporary Road Closures (TRCs)**

Please be aware, that *DCC Roadworks’ Contractor*, *Circet Networks (Ireland)*,

(and following discussion(s) with various *Stakeholders*, and including:-

*DCC Traffic Division,*

*DCC Fire Brigade – Dublin Fire Brigade [DFB],*

*An Garda Síochána [AGS], and*

*LUAS – both Owner, Tii,* and *Operator, TransDev*)

has applied for,

and reasonably expects to successfully obtain proposed, so-called ‘*Temporary Road Closures’* [TRCs]

and all such TRCs as here-indicated in the *Table* immediately below:-

|  |  |  |  |
| --- | --- | --- | --- |
| **ID No.** | **Location and Extent** | **Timing and Duration** | **Works** |
| 1 | South Anne St  (Grafton St to Anne’s Ln) | 22/09/2025 for 8 weeks | Works (Utilities and Paving) …from Grafton Street to Anne’s Lane. |

4.            **Deliveries & Access**

Deliveries to premises on South Anne Street will be facilitated via the eastern end of South Anne Street and Grafton Street. If you have specific access needs, please contact the contractor directly.

If you or someone you know is affected by these works and requires assistance, please reach out:

Turlough Nolan – [turlough.nolan@circet.ie](mailto:turlough.nolan@circet.ie)

We appreciate your cooperation and understanding as we work to enhance the public realm in this vibrant part of Dublin. Both Dublin City Council and Circet Networks (Ireland) are committed to maintaining a positive and collaborative relationship with all stakeholders throughout the duration of the project.